## Summary Report
Summary Testing Report
Project Name |  | HDS Assignment |  |  | Current Sprint |  |  | Sprint 1
Project Manager |  | N/a |  |  | Test Period |  |  | 07/01/2025 - 07/01/2025
|  | Function Name | Status
|  | US - 01 | Done
|  | US - 02 | Done
Done
|  | Total | In Progress | Done
|  | 3 | 0 | 3
2. Manual test case status
[6 empty] | Status |  | Comment
[6 empty] | Pass | 3
[6 empty] | Fail | 10
[6 empty] | Not Started | 0
[6 empty] | Total | 13
Noted issues: - There's no error message defined for each invalid cases - All test cases with invalid data have failed
3. Automation Test
|  | Build Number | N/a
|  | Enviroment execution | Test
|  | Time execution | 2 hours
|  | Automation Coverage | Comment |  |  | Automation Test (High Level) |  | Comment
|  | Manual TCs | 13 |  |  | Pass | 2 | - All test cases with invalid data have failed.
|  | Automation TCs | 6 |  |  | Fail | 4
|  | Total |  |  |  | Block | 0
[6 empty] | Total | 6
Critical Defects
Jira ID | Title |  |  |  |  | Status | Comment
Bug_02 | Wrong response when user send request with no uploaded image file |  |  |  |  | Open
Bug_04 | Wrong status code when user send request file with empty folder |  |  |  |  | Open
Bug_05 | Wrong status code and body response when user send request file that's not a zip file |  |  |  |  | Open
Remark

## Q&A
No | User Story | Questions | Answers
1 | US-01 | Do we have any sample error message in those cases: - User upload invalid file type - User upload corrupted/ empty file - User haven't upload any file
2 | US-01 | Do we have any limit for file size? Example: picture file size must not exceed 10MBs
3 | US-01 | Can this API handle case that uploaded file have been failed? Ex: failed to upload images on image server...
4 | US-02 | Do we have any sample error message in those cases: - User upload invalid file type (ex: .ziq, .pdf...) - User upload corrupted/ empty file - User haven't upload any file - Zip file didn't contain valid file - Zip file contained folder only ...
5 | US-02 | What's the expected behavior of this API when we upload Zip file contain both valid and invalid files?
6 | US-02 | Do we have any limit for Zip file size? Example: Zip file size must not exceed 50MBs

## User Story 1
Module | Upload File |  |  |  | Test result
Test requirement | Store and use my pictures |  |  |  | Passed | 1
TC_ID | TC |  |  |  | Failed | 6
Reference Jira | <Jira> |  |  |  | N/A | 0
ID | Summary | Pre-condition | Steps | Expect | Test Type (*) | Priority | Test result | Automated | Tester | Note
TC_01 | Allow an Anonymous user to upload the valid picture files | 1, POST request: https://assessement.onrender.com/api/image 2, All valid image files in test data folder | 1. Send the POST request to upload each valid image files 2. Verify the status code 3. Verify the body response 4. Ctr+click on the image link | 2. Status code should be 200 3. Body response should have: - "image" field - Permanent link for valid image files 4. Image link should be worked and display correct image | Functional | High | Passed | Yes
TC_02 | Do not allow an Anonymous user to upload invalid image format | 1, POST request: https://assessement.onrender.com/api/image 2. Upload .pdf file in test data | 1. Send the POST request with any invalid file 2. Verify the status code 3. Verify the body response | 2. Status code is 400 3. the body response should have "err" field with the message: "File isn't an image" | Functional | High | Failed | Yes |  | Bug_01
TC_03 | Do not allow an Anonymous user to upload corrupted image file | 1, POST request: https://assessement.onrender.com/api/image 2. Upload corrupted image file in test data | 1. Send the POST request with any invalid file 2. Verify the status code 3. Verify the body response | 2. Status code is 400 3. the body response should have "err" field with the message: "The uploaded file cannot be processed" | Functional | Low | Failed | No
TC_04 | Do not allow an Anonymous user to upload without an image file | 1, POST request: https://assessement.onrender.com/api/image | 1. Send the POST request with no uploaded file 2. Verify the status code 3. Verify the body response | 2. Status code is 400 3. the body response should have "err" field with the message: "No file provided in the request" | Functional | High | Failed | Yes |  | Bug_02
TC_05 | Do not allow to upload multiple files at the same time | 1, POST request: https://assessement.onrender.com/api/image 2..Upload multiple valid images in test data. | 1. Send the POST request to upload multiple images at the same time 2. Verify the status code 3. Verify the body response | 2. The status code should be 400 3. the body response should have "err" field with the message: "Cannot upload multiple files at once" | Functional | Medium | Failed | No
TC_06 | Do not allow an Anonymous user to upload a valid file with exceeded file size | 1, POST request: https://assessement.onrender.com/api/zip 2, Image file is > 10MB | 1.Send the POST request with exceeded image file 3. Verify the status code 4. Verify the body response | 3. Status code should be 400 4. The body response should have "err" field with the message: "The uploaded file exceeds the maximum allowed size of 10 MB" | Functional | Medium | Failed | No
TC_07 | Do not allow user to send request with wrong method | 1, POST request: https://assessement.onrender.com/api/image | 1. Change the method from POST to any method as GET/ PUT/ DELETE 2. Send request with valid image file in body request 3. Verify the status code 4. Verify the body response | 2. The status code should be 405 3. The body response should have "err" field with the message: "This method is not allowed" | Functional | Low | Failed | No |  | Bug_03

## User Story 2
Module | Upload File |  |  |  | Test result
Test requirement | Uploading my pictures multiple times |  |  |  | Passed | 2
TC_ID | TC |  |  |  | Failed | 4
Reference Jira | <Jira> |  |  |  | N/A | 0
ID | Summary | Pre-condition | Steps | Expect | Test Type (*) | Priority | Test result | Automated | Tester | Note
TC_01 | Allow an Anonymous user to upload an zip file containing multiple valid image files | 1, POST request: https://assessement.onrender.com/api/zip 2,Valid zip file in test data folder | 1.Send the POST request to upload the zip file 2. Verify the status code 3. Verify the response body 4. Ctr+click randomly on the list of image links | 2. Status code should be 200 3. Body response should have: - "images" field - Correct number of permanent link for valid image files, respectively with the number of image files in the uploaded file - No duplicated image links in the response 4. Image link should be worked and display correct image | Functional | High | Passed | Yes
TC_02 | Allow an Anonymous user to upload a zip file contains both valid and invalid file | 1, POST request: https://assessement.onrender.com/api/zip 2. Zip file contains both valid and invalid file | 1.Send the POST request to upload the zip file 2. Verify the status code 3. Verify the response body 4.Ctr+click randomly on the list of image links | 2. Status code should be 200 3. Body response should have: - "images" field - Correct number of permanent link for valid image files, respectively with the number of valid image files in the uploaded file - Do not include link for invalid image files - No duplicated image links in the response 4. Image link should be worked and display correct image | Functional | Medium | Passed | No
TC_03 | Do not allow an Anonymous user to upload an empty zip file | 1, POST request: https://assessement.onrender.com/api/zip 2,Empty zip file in test folder | 1.Send the POST request to upload the zip file 3. Verify the status code 4. Verify the body response | 3. Status code should be 400 4. the body response should have "err" field with the message: "no image found in zip file" | Functional | High | Failed | Yes |  | Bug_04
TC_04 | Do not allow an Anonymous user to upload an zip file contains only invalid image files | 1, POST request: https://assessement.onrender.com/api/zip 2,Zip file contains only invalid files( ex: .pdf/.exe/ etc) in test folder | 1.Send the POST request to upload the zip file 3. Verify the status code 4. Verify the body response | 3. Status code should be 400 4. The body response should have "err" field with the message: "no image found in zip file" | Functional | Medium | Failed | No
TC_05 | Do not allow an Anonymous user to upload invalid zip file format | 1, POST request: https://assessement.onrender.com/api/zip 2, Invalid zip file in test data folder | 1.Send the POST request with any non zip file 3. Verify the status code 4. Verify the body response | 3. Status code should be 400 4. The body response should have "err" field with the message: "File isn't a zip" | Functional | High | Failed | Yes |  | Bug_05
TC_06 | Do not allow an Anonymous user to upload a zip file with exceeded file size | 1, POST request: https://assessement.onrender.com/api/zip 2, Zip file is > 50MB | 1.Send the POST request with exceeded zip file 3. Verify the status code 4. Verify the body response | 3. Status code should be 400 4. The body response should have "err" field with the message: "The uploaded file exceeds the maximum allowed size of 50 MB" | Functional | Medium | Failed | No

## Bug report
Bug no | Bug title | Severity | Pre-conditions | Steps | Current result | Expected result | Note
Bug_01 | Wrong status code and body response when user send request with invalid file | Medium | 1, POST request: https://assessement.onrender.com/api/image 2,pdf file in test data | 1. Send the POST request with any invalid file 2. Verify the status code 3. Verify the body response | 2. Return status code: 500 - Internal Server Error 3. The body response with: "err": "File isn' an image" | 2. Should return with status code: 400 3. The body response with: "err": "File isn't an image"
Bug_02 | Wrong response when user send request with no uploaded image file | Critical | 1, POST request: https://assessement.onrender.com/api/image 2,no file value | Send the POST request with no uploaded file | Return status code: 500 - Internal Server Error | - Should return with status code 400 - The body response should have ""err"" field with the message: ""No file provided in the request
Bug_03 | Wrong status code when user send request with wrong method | Medium | Request: https://assessement.onrender.com/api/image | Change the method from POST to any method as GET/ PUT/ DELETE and send request | Return with status code: 404 Not Found | - Should return with status code 405 - The body response should have "err" field with the message: "This method is not allowed"
Bug_04 | Wrong status code when user send request file with empty folder | Critical | 1, POST request: https://assessement.onrender.com/api/zip 2,Empty zip file in test folder | 1. Send the POST request with a zip file with no image file inside 2. Verify the status code 3. Verify the body response | 2. Return with status code: 500 - Internal Server Error 3. The body response with: "err": "no image found in zip file" | 2. Should return with status code: 400 3. The body response with: "err": "no image found in zip file"
Bug_05 | Wrong status code and body response when user send request file that's not a zip file | Critical | 1, POST request: https://assessement.onrender.com/api/zip 2, Invalid zip file in test data folder | 1. Send the POST request with a non-zip file 2. Verify the status code 3. Verify the body response | 2. Return with status code: 403 Forbidden 3. The body response with: "err": "File isn' a zip " | 2. Should return with status code: 400 3. The body response with: "err": "File isn't a zip "

## Change History (hidden)
Records of Change
No | Date | Effective Date | Changed Item | Types (A, M, D) | Change Description | Version
1 | 2020-04-10 | 2022-02-16 | Create new | Create new | Create new | 1.0
2 | 2023-05-16 |  |  | M | Update new VMO's new logo | 1.1